## Complexity of assigment
Each of the parameters is assessed and given a value (integer) from 1 (not complex) to 4 (very complex).
Fields with this color are filled in by the candidate
AX <Name of the assignment>
Parameter | Description of complexity 1 | Description of complexity 4 | Scoring | Motivation
Capability-based indicators
Objectives, results and outcomes | Well-defined project objectives and scope. The goals do not conflict with other requirements, strategies and goals | The objectives and scope are unclear and uncertain. Many conflicts with other stakeholders and organisation s' goals, strategies, expectations and needs.
Processes, methods, tools and techniques | The work has strong support from a process model, governance model and organisation 's project maturity is high. | Processes, methods and templates are not available. The assignment has to create its own. The governance model is non-existent or diffuse. The organisation 's maturity is low.
Resources including financial | The assignments resources are clear, available and sufficient. There are identified personal resources and the work is funded with uncertainty margins. | It is unclear where the financial resources are to be taken and how this is done. The number of allocations are many and the employees have many different responsibilities outside the assignment. The availability of resources is unclear.
Risks and opportunities | The uncertainty is small, few risks and few opportunities that may affect the work | The assignment is unique and pioneering. There are many risks with major consequences and difficult to estimate the probability. But there are also several interesting opportunities that the assignment should utilize.
Contextual indicators
Relations with the permanent organi-sation | The assignment is well integrated and anchored within the organisation. All stakeholders are clearly defined and appointed. | The assignment is not integrated with the organisation , resistance and unwillingness are not uncommon, it is unclear who will receive the results.
Stakeholders and integration | There are few stakeholders and they can easily be managed in groups. They have little impact on the assignment. | The assignment has many stakeholders also outside the organisation. They have different interest areas and have great impact on the outcome.
Cultural and social context | The team is a homogeneous group that works in an organisation without major cultural differences. The team sits together geographically. | There are major cultural differences within the assignement, and also between different stakeholders. The assignment works in a geographically widely distributed organisation with large time differences and different native languages.
Management and leadership-based parameters
Leadership, teamwork and decisions | The team's degree of maturity is high. The team works easily together towards the same goal | The team has a very low degree of maturity. The team spirit is low and it is difficult with cross-border cooperation. It is hard to get a holistic view of how the employees work. "Silo-thinking" prevails. It is hard to make decisions
The degree of innovation and general circum-stances | The assignments results are clear and without major new development, innovative thinking or new working methods | The result of the assignment is partly unknown, brand new technology or revolutionary new processes.
Need to coordinate and defend the interests of the assignment | The assignment has few or no interfaces with other projects, businesses or stakeholders. Little or no co-planning is required. | The assignment is carried out in an environment where much coordination and co-planning with others are required. Negotiations with and the influence of others are required to carry out the assignment within the frames of time and economics.
Complexity of the assignment, the sum of the assessment |  |  | 0
The complexity of the assignment
Complexity
Complexity is valuated using ten parameters under three headings. Each of the parameters is assessed and given a value (integer)
from 1 (not complex) to 4 (very complex)
The complexity must be assessed from your perspective as a leader. Only conditions handled by management are relevant. The complexity of the assignment is then calculated as the sum of the values ​​of the ten parameters.
The complexity must meet the following criteria per level
Level A >= 32 (very complex)
Level B >= 25 (complex)
Level C >= 16 (moderately complex)
Level D No requirements